## Hoja1
Estimación Basada en puntos de casos de uso
Unadjusted Use Case Weight
Use case complexity | Number of transactions | Weight
Simple | 3 or fewer | 5
Average | 4 to 7 | 10
Complex | More than 7 | 15
Table 1. Use case weights based on the number of transactions.
SauveGuard
Use case complexity | Weight | Number of use cases | Product
Simple | 5 | 10 | 50
Average | 10 | 4 | 40
Complex | 15 | 0 | 0
Total |  |  | 90
Table 2. Calculating Unadjusted Use Case Weight (UUCW) for SauveGuard.
Unadjusted Actor Weight
Actor Type | Example |  | Weight
Simple | Another system through an API |  | 1
Average | Another system through a protocal |  | 2
A person through a text-based user interface
Complex | A person through through a graphical user interface |  | 3
SauveGuard
Use case complexity | Use Case | Weight | SauveGuard | Product
Simple | API | 1 | 0 | 0
Average | Comunication Protocol | 2 | 0 | 0
Complex | GUI | 3 | 2 | 6
Total |  |  |  | 6
Table 3. Complexity for the SauveGuard mainly use cases.
UUCP = UUCW + UAW |  | UUCP = | 96
Adjusting For Technical Complexity
Factor | Description | Weight
T1 | Distributed system | 2
T2 | Performance objectives | 2
T3 | End-user efficiency | 1
T4 | Complex processing | 1
T5 | Reusable code | 1
T6 | Easy to install | 0.5
T7 | Easy to use | 0.5
T8 | Portable | 2
T9 | Easy to change | 1
T10 | Concurrent use | 1
T11 | Security | 1
T12 | Access for third parties | 1
T13 | Training needs | 1
Table 5. The weight of each factor impacting technical complexity.
SauveGuard
Factor | Description | Weight | SauveGuard | Total
T1 | Distributed system | 2 | 2 | 4
T2 | Performance objectives | 2 | 4 | 4
T3 | End-user efficiency | 1 | 3 | 3
T4 | Complex processing | 1 | 2 | 2
T5 | Reusable code | 1 | 3 | 3
T6 | Easy to install | 0.5 | 4 | 2
T7 | Easy to use | 0.5 | 5 | 2.5
T8 | Portable | 2 | 5 | 10
T9 | Easy to change | 1 | 4 | 4
T10 | Concurrent use | 1 | 2 | 2
T11 | Security | 1 | 2 | 2
T12 | Access for third parties | 1 | 0 | 0
T13 | Training needs | 1 | 2 | 2
Total | - | - |  | 40.5
Table 5. The weight of each factor impacting technical complexity.
TCF = 0.6 + (0.01 x TFactor) |  | TCF = | 1.005
Adjusting For Environmental Complexity
Factor | Description |  | Weigh
E1 | Familiar with the development process |  | 1.5
E2 | Application experience |  | 0.5
E3 | Object-oriented experience |  | 1
E4 | Lead analyst capability |  | 0.5
E5 | Motivation |  | 1
E6 | Stable requirements |  | 2
E7 | Part-time staff |  | -1
E8 | Difficult programming language |  | -1
Table 7. Environmental factors and their weights
SauveGuard
Factor | Weight | Assessment | Impact
Familiar with the development process | 1.5 | 3 | 4.5
Application experience | 0.5 | 0 | 0
Object-oriented experience | 1 | 5 | 5
Lead analyst capability | 0.5 | 2.5 | 1.25
Motivation | 1 | 5 | 5
Stable requirements | 2 | 4 | 8
Part-time staff | -1 | 0 | 0
Difficult programming language | -1 | 3 | -3
Total | - | - | 20.75
EF = 1.4 + (-0.03 x EFactor) |  | EF = | 0.7775
UCP = UUCW x TCF x EF |  | UCP = | 70.3249
a
Factor | Description | Weight
UUCW | Unadjusted Use Case Weigh | 90
UAW | Unadjusted Actor Weight | 6
TCF | Technical Complexity Factor | 1.005
EF | Environmental Factor | 0.7775
Overall Project
Number of hours the team will average use case point |  | 23 | hours
Total Hours |  | 1617.4721 | hours
Total Developers |  | 5 | persons
Hours per week for each developer |  | 30 | hours
Total Hours per Week |  | 150 | hours
Iteration Duration |  | 3 | weeks
Hours of progress per iteration |  | 450 | hours
Overall Project Duration |  | 3.5944 | three-week iteration
Overall Project Duration (Months) |  | 2.6958 | months
Costo Proyecto de Ingeniería de Software
Datos de entrada | Costo | Periodo
Sueldo Ingeniero | 2500000 | mes
Sueldo Ingeniero (Dia) | 83333.3333 | dia
Número Ingenieros | 5 | personas
Factor Prestacional | 50% | mes
Arriendo Oficina | 0 | mes
Arriendo en la nube | 0 | mes
Internet | 0 | mes
Energía | 0 | mes
Acueducto | 0 | bimensual
Auxiliar Contable | 0 | mes
Servicio de Contabilidad | 0 | mes
Registro Mercantil | 700000 | anual
Transporte | 125000 | mes
Almuerzo | 1000000 | mes
Antojos | 100000 | mes
Udemy | 66000 | (pago único)
Tx | 33% | anual
Proyección Financiera (Mensual)
Gastos Propios de Desarrollo
Nómina
Sueldo básico ingenieros | 12500000
Factor prestacional | 6250000
Total Nómina | 18750000
Suministros
Transporte | 125000
Almuerzo | 1000000
Antojos | 100000
Total Suministros | 1225000
Arriendos
Arriendo oficina | 0
Arriendo en la nube | 150000
Total Arriendos | 150000
Servicios Públicos
Internet | 0
Energía | 0
Acueducto | 0
Total Servicios Públicos | 0
Total Gastos Propios de Desarrollo | 20125000
Gatos Administrativos
Auxiliar contable | 0
Factor prestacional | 0
Nómina | 0
Servicio de Contabilidad | 0
Total Gastos Administrativos | 0
Inversión Inicial
Udemy | 66000
Registro Mercantil | 58333.3333
Total Inversión Inicial | 124333.3333
Total Proyección Financiera | 20249333.3333
Impuestos
Tx | 2.75%
Total Impuestos | 556856.6667
Total Costo Mensual | 20806190
Total Costo Proyecto de Ingeniería de Software
56089053.9208